## EAT
ECSS Applicability Table (EAT)
Project/Programme |  | Mission Type
Contract Information |  | Issue Date
Originator |  | Event Generation
Standard | Applicalbility (A/T/>>/NA) | Justification/Clarification (including justification/clarification of the use of other standard instead of
ECSS-M-ST-10C Rev1 | T | Standard made applicable to regulate the project management effort. Tailored to fit project type characteristics and scale
ECSS-M-ST-10-01 | T | Standard made applicable to regulate the conduct of reviews as a method to assess milestone achieval and stablish both student and supervisor responsabilities in the matter. Tailored to adapt complexity to characteristics of project type
ECSS-M-ST-40C Rev1 | T | Standard made applicable to include the minimal requirements regarding configuration and information management for projects of the type. Tailored to include only the most relevant in terms of project de-risking and best practices to be transmitted from an educational point of view
ECSS-M-ST-60C | T | Standard made applicable to compliment the budget and scheduling requirements stablished in ECSS-M-ST-10C Rev.1. Tailored to only include the strictly necessary requirements for the projects of the type
ECSS-M-ST-80C | T | Standard made applicable to regulate risk management and risk policy for projects of the type. Tailored to clearly state the requirements applicable to the students and those applicable to supervisors.
ECSS-E-ST-10C Rev1 | T | Standard made applicable to regulate the Systems Engineering actions carried out for the projects of the type. Tailored to adapt the scope of applicabilityn, DRDs implemented and regulate the distribution of responsabilities between students and supervisors regarding the SE duties
ECSS-E-ST-10-02C Rev1 | T | Standard made applicable to regulate the verification planning and associated activities for projects of the type. Tailored to de-scope the activities in relation to the project's characteristics and to adapt the implemented DRDs
ECSS-E-ST-10-06C | T | Standard made applicable to regulate the generation and management of technical requirements for projects of the type. Tailored to adapt applicable DRDs.
ECSS-E-ST-10-24C Rev1 | A | Standard made applicable to regulate project interaction with interfaces and platforms for the project type

## EARM
ECSS Applicability Requirement Matrix (EARM)
Project/Programme |  |  | Standard Reference |  | A=Applicable | * Requirement made applicable only to the academic entities and Gov./Agency/Industrial stakeholders supervising and/or sponsoring the project
Contract Information |  |  | Issue Date |  | M=modified
Originator |  |  | Event Generation |  | D=Deleted
Product Type |  |  |  |  | N= New
1. ECSS Standard | 2. ECSS Req. Identifier | 3. Applicability (A/M/D/N) | 5. Modified or New Requirement | 6. Justification/Clarification | Requirement Superclasses
ECSS-M-ST-10C Rev1 | 5.1.2.a | M* | Each customer shall prepare business agreements (ITT’s, RFP’s, or RFQ’s), including the project requirements documents (PRD) to be made applicable between him and all non student supplier(s) | Clear and formal agreements between the stakeholders of the projects, on behalf of the students are required for the correct development of the project from a legal, educational, managerial and technical point of view. This requirements addresses in particular relationships between main customer and academic institutions and/or industrial stakeholders such as platform providers | General Buisness law of the land
ECSS-M-ST-10C Rev1 | 5.1.2.a.1 | N | The student supplier shall prepare alongside the customer all project requirement documents (PRD) to be made applicable between them and the customers excepting Statement of Work, Product Assurance requirements, programmatic requirements, and Tender requirements | The definition of most technical, management and engineering requirements are a responsibility of the student team as project developpers given the relationship with their customers. Customers are to be involved in the process both for ensured compliance to their requirements and for stewardship of the students
ECSS-M-ST-10C Rev1 | 5.1.2.b | A |  | Made applicable as all parties shall employ ECSS as per the premise and nature of the tailoring activity conducted and the educational objectives observed.
ECSS-M-ST-10C Rev1 | 5.1.2.c | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.1.2.d | A |  | Applicable. This tailoring activity addresses this requirement partially.
ECSS-M-ST-10C Rev1 | 5.1.2.e | A |  | Applicable.
ECSS-M-ST-10C Rev1 | 5.1.2.f | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.1.2.g | D |  | As per the project type definition, there is only one level of Customer-Supplier chain considered in the tailoring activity
ECSS-M-ST-10C Rev1 | 5.1.3.a | M* | Each non student supplier in the customer‐supplier chain shall prepare a project management plan (PMP) in conformance with Annex A. | The PMP DRD proposed by ECSS-M-ST-10C Rev1 is applicable to all non student suppliers. For the student team, a tailored version of the PMP is requested | Project management Function and PMP
ECSS-M-ST-10C Rev1 | 5.1.3.a.1 | N | The student team shall prepare a project management plan (PMP) in conformance with ECSS M ST 10C Annex A | The student team is requested to prepare a PMP in accordance to a tailored DRD
ECSS-M-ST-10C Rev1 | 5.1.3.b | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.2.1.1a | M* | Each customer and supplier (the academic endorsing entity shall represent the student team as supplier) shall define the authority for project management and business agreement signing | Applciable, but through the mediation of the academic endorsing entity.
ECSS-M-ST-10C Rev1 | 5.2.1.1.b | A |  | Applicable, particulalry in relation to platforms
ECSS-M-ST-10C Rev1 | 5.2.1.1.c | A |  | Applicable, but expected to affect customers in the vast majority of cases
ECSS-M-ST-10C Rev1 | 5.2.1.1.d | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.2.1.2.a | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.2.1.2.b | M | The supplier shall nominate a team member as a project manager | The project management function shall be carried out unequivocally by one of the students, even if aided by the rest of team components.
ECSS-M-ST-10C Rev1 | 5.2.1.2.c | M | The supplier shall ensure that the project manager has the authority to execute all tasks needed to comply to all other applicable requirements related to project management | The project manager has to be able to manage the project, requiring thus authority to steer the project as need towards compliance to the PRD stablished with the customer
ECSS-M-ST-10C Rev1 | 5,2.1.2.d | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.2.1.2.e | A |  | Applciable
ECSS-M-ST-10C Rev1 | 5.2.1.2.f | D |  | Exceeds the scope of the project type
ECSS-M-ST-10C Rev1 | 5.2.1.2.g | D |  | Eceeds the scope of the project type
ECSS-M-ST-10C Rev1 | 5.2.1.2.h | D |  | Exceeds the scope of the project type
ECSS-M-ST-10C Rev1 | 5.2.2.1.a | A |  | Applicable. The customer shall define the reproting system and action monitoring expected from the students | Communications, Customer/Supplier Meetings and reporting
ECSS-M-ST-10C Rev1 | 5.2.2.1.b | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.2.2.1.c | A |  | Applicable. Additionally, regularly scheduled update meetings are an integral aspect of the educational return expected from the project .
ECSS-M-ST-10C Rev1 | 5.2.2.1.d | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.2.2.1.e | M | Customer‐supplier meetings should be based on an agreed written agenda | Whilst a good practice, this tailoring has as driven element not to over constraining the relationship between student teams and their customers
ECSS-M-ST-10C Rev1 | 5.2.2.1.f | D |  | Whilst a good practice, this tailoring has as driven element not to over constraining the relationship between student teams and their customers
ECSS-M-ST-10C Rev1 | 5.2.2.1.g | M | The results of the meeting shall be documented in minutes of Meeting maintained by the student team | Correct management and upkeep of meeting minutes is a useful educational return provided by the project type. However, minutes are not to be required to be signed and approved after each meeting to not overconstrain the relationship between students and customers. The meetings will be held obeserving a good faith approach and the customers may provide inputs to both clarify the specific klisted notes and improve the quality of their preparation
ECSS-M-ST-10C Rev1 | 5.2.2.1.h | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.2.2.1.i | M | Each action shall be assigned a responsible, a definition, and a due-date at minimum | Whislt the original requirmenent ensure correct traceability, the degraded form proposed ensures tat the core concept is learnt whilst not encumbering the stablishment of actions in the meetings.
ECSS-M-ST-10C Rev1 | 5.2.2.1.j | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.2.2.1.k | D |  | Out of scope of the project type
ECSS-M-ST-10C Rev1 | 5.2.2.2.a | D |  | Deleted in deference of more scope appropiate reporting requirements
ECSS-M-ST-10C Rev1 | 5.2.2.2.b | D |  | Deleted in deference of more scope appropiate reporting requirements
ECSS-M-ST-10C Rev1 | 5.2.2.2.c | D |  | Deleted in deference of more scope appropiate reporting requirements
ECSS-M-ST-10C Rev1 | 5.2.2.2.a.1 | N | The student team shall report progress during regular meetings and written communications with the customer | No formal reporting is required beyond the meetings and the milestone reviews. Regular reporting is degraded into the tag-up meetigs of the project and its corolary communications
ECSS-M-ST-10C Rev1 | 5.2.2.2.c.1 | N | The student team shall notify the customer of any significant deviation or anomalous circustance impacting project development | The student team is expected to otify ist stakeholders of any substantial deviation from the expected progress timeline so as to allow timely countermeasures and extra support being provided to the team.
ECSS-M-ST-10C Rev1 | 5.2.3.1.a | D |  | Audits are considered out-of-scope for the project-type | Audits
ECSS-M-ST-10C Rev1 | 5.2.3.1.b | D |  | Audits are considered out-of-scope for the project-type
ECSS-M-ST-10C Rev1 | 5.2.3.1.c | D |  | Audits are considered out-of-scope for the project-type
ECSS-M-ST-10C Rev1 | 5.2.3.1.d | D |  | Audits are considered out-of-scope for the project-type
ECSS-M-ST-10C Rev1 | 5.2.3.2.a | D |  | Audits are considered out-of-scope for the project-type
ECSS-M-ST-10C Rev1 | 5.2.3.3.a | D |  | Audits are considered out-of-scope for the project-type
ECSS-M-ST-10C Rev1 | 5.2.3.3.b | D |  | Audits are considered out-of-scope for the project-type
ECSS-M-ST-10C Rev1 | 5.2.3.3.c | D |  | Audits are considered out-of-scope for the project-type
ECSS-M-ST-10C Rev1 | 5.2.3.3.d | D |  | Audits are considered out-of-scope for the project-type
ECSS-M-ST-10C Rev1 | 5.2.3.3.e | D |  | Audits are considered out-of-scope for the project-type
ECSS-M-ST-10C Rev1 | 5.3.a | M | The supplier shall develop the product tree for his products down to the deliverable end items, incorporating the product trees of each of his lower tier suppliers, in conformance with Annex B andECSS-E-ST-10C Rev1 Annex B.1 | Product tree is to be employed in a degraded form to retain functionality without increasing unnecesarily the documention load given the project scope. Product tree is maintained for its educational value. | Product Tree
ECSS-M-ST-10C Rev1 | 5.3.b | M | The product tree shall be established in a preliminary version at start of phase B and finalized not later than CDR | Applicable. Final DR is expected by CDR. Given the project-type configuration control becomes more realistic after Phase C
ECSS-M-ST-10C Rev1 | 5.3.c | A |  | Applicable.
ECSS-M-ST-10C Rev1 | 5.3.d | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.3.e | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.3.f | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.3.g | M | The supplier shall maintain the product tree up‐to‐date under configuration control past its approval in CDR. | Applicable. Final DR is expected by CDR. Given the project-type configuration control becomes more realistic after Phase C
ECSS-M-ST-10C Rev1 | 5.3.h | M | The supplier shall establish the work breakdown structure (WBS) for his work share, incorporating the WBS to the ECSS M ST 10C Annex A | WBS is expected as part of the PMP | WBS
ECSS-M-ST-10C Rev1 | 5.3.i | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.3.j | D |  | Given the degraded nature of the product tree in this tailoring activity, the enforceability of direct connection of WBS and PT becomes too difficult to actually carry out into practice
ECSS-M-ST-10C Rev1 | 5.3.k | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.3.l | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.3.m | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.3.n | M | The supplier shall establish work package (WP) descriptions for each work package shown in his WBS containing, at minimum, WP title, unique identifier, WP manager, WP objectives description, Description of WP tasks, list of expected outputs and deliverables | A degraded version of the WP description provided in ECSS-M-ST-10C rev1 Annex D is enforced to retain the critical information to not overencumber the project amnagement function and retain the educational value of the WBS
ECSS-M-ST-10C Rev1 | 5.3.n.1 | N | Each task conatined in a WP shall have a task description containing at minimum, objectives of task, deliverables of task (if any), task responsible and expected task duration | Additional requirements for task description are provided to ensure the WBS is developped in a meaningful from an educational point of view.
ECSS-M-ST-10C Rev1 | 5.3.o | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.3.p | D |  | An OBS delivery will not be enforced. The organizational structure breakdown will be provided as a section of the PMP | OBS
ECSS-M-ST-10C Rev1 | 5.4.a | A |  | Applicable | Project Phasing
ECSS-M-ST-10C Rev1 | 5.4.a.1 | N | The customer shall stablish what reviews are applicable for the project taking into account the project's characteristics. | Given the scope of the project type, the employement of all ECSS mandated reviews may be out-of-scope for the project type. Responsibility lies on the customer to stablish the required reviews
ECSS-M-ST-10C Rev1 | 5.4.a.2 | N | The customer shall enforce at minimum one design review bfore progressing into AIT activities | The students shall be enforced to break down development into pre and post design freeze, with at least one Design review acting as the turning point. This requirement is based on the educational return expected from this tailoring activity
ECSS-M-ST-10C Rev1 | 5.4.a.3 | N | The customer shall enforce at minimum one Acceptance Review (or equivalent review for project scope) before progressing to operations | The students shall be enforced to have a formal approval before proceeding to operations. This requirement is based on the educational return expected from this tailoring activity, as well as overall safety of the project. This review shall act as a failsafe against potential issues to professional customers and/or suppliers due to development erros made by the students.
ECSS-M-ST-10C Rev1 | 5.4.b | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.4.c | A |  | Applicable
ECSS-M-ST-10C Rev1 | 5.4.d | A |  | Applicable
ECSS-M-ST-10C Rev1 | Annex A | M | Modified DRD for PMP is available inECSS M ST 10C Annex A | PMP DRD is modfied to adapt to scope of project type and applicable requirements included in this EARM | Project Management DRD
ECSS-M-ST-10C Rev1 | Annex B | D |  | The DRD for the PT is no longer enforceable as of itself. Refer to ECSS-M-ST-10C Rev1 5.3.a for further information
ECSS-M-ST-10C Rev1 | Annex C | M | DRD is applicable but included in a degraded form in the PMP DRD | Refer to the PMP DRD provided in Annex [REF] for more information
ECSS-M-ST-10C Rev1 | Annex D | D |  | DRD deleted in favor of ECSS-M-ST-10C Rev1 5.3.n
ECSS-M-ST-10C Rev1 | Annex E | D |  | No format is enforced a priori for reporting activities
ECSS-M-ST-10-01C | 5.1.a | A |  | Applicable | Review general requirements
ECSS-M-ST-10-01C | 5.1.b | A |  | Applicable
ECSS-M-ST-10-01C | 5.1.c | A |  | Applicable
ECSS-M-ST-10-01C | 5.1.d | A |  | Applicable
ECSS-M-ST-10-01C | 5.1.e | A |  | Applicable
ECSS-M-ST-10-01C | 5.2.a | A |  | Applicable | Review Panel
ECSS-M-ST-10-01C | 5.2.a.1 | N | The review authority, customer and consumer can be the same entity partally or totally (except for provisions stating stricly the opposite such as ECSS M ST 10 01C 5.2.c) | Given the scope of the project type and the particular position as stakeholders of the project the customer has the authority if needed to act as consumer and review authority of the project
ECSS-M-ST-10-01C | 5.2.b | A |  | Applicable
ECSS-M-ST-10-01C | 5.2.c | A |  | Applicable
ECSS-M-ST-10-01C | 5.2.d | M | The review team shall include representatives of the consumer organization having no direct involvement in the project activities, excepting supervising individuals belonging to the consumer entity after the proclamation of No Conflict of Interest to the review panel chair | This requirement is modified to allow the inclusion of the supervisors/interfaces with the students from the customer side, as in most cases given the scope of the project the conflict of interest can be waived and the availability of a completely independent review team would make the review process unfeaseable. Moreover, the proximity and familiarity with the project can and should enhance the educational return of the process. The supervisors are considered, in good faith, capable of acting in the interest of the customer despite personal investment on the project and student team.
ECSS-M-ST-10-01C | 5.3.1.a | A |  | Applciable
ECSS-M-ST-10-01C | 5.3.1.b | A |  | Applicable
ECSS-M-ST-10-01C | 5.3.1.c | A |  | Applicable
ECSS-M-ST-10-01C | 5.3.1.d | A |  | Applicable
ECSS-M-ST-10-01C | 5.3.1.e | M | The review authority shall make recommendations to the student team as supplier | Given the special role of the student team as suppliers but also main proposers of the project, and due to the scope of the project type, the review recommendations can be transmitted directly to the supplier student team
ECSS-M-ST-10-01C | 5.3.1.f | M | The review authority shall report its findings and final recommendations in a document that presents clearly its conclusions, remaining open actions, recommendations and overall stance on approval of the review | Modified to simplify the result reporting of the review in accordance to the scope of the project type. The main philosophy of the process is kept for educational purposes, but formality is reduced to not overencumber the process.
ECSS-M-ST-10-01C | 5.3.2.a | M | The customer shall propose a procedure for the review conforming to [REQ DRD Review] for review authority approval. | An adapted DRD for the Review process is in order given the scope of the project. The linked DRD requirement presents a more streamlined and adequate procedure in terms of sizing and complexity
ECSS-M-ST-10-01C | 5.3.2.b | A |  | Applicable
ECSS-M-ST-10-01C | 5.3.2.c | A |  | Applicable
ECSS-M-ST-10-01C | 5.3.3.a | A |  | Applicable | Reviewed Student Team
ECSS-M-ST-10-01C | 5.3.3.b | A |  | Applicable
ECSS-M-ST-10-01C | 5.3.3.c | M | The supplier shall provide responses to RIDs and collaborate in proposing a schedule for the identified actions. | Modified to better stablish the role of the student team as supplier given the special relationship stablished with the review team and customer and their potential overlap
ECSS-M-ST-10-01C | 5.3.3.c.1 | N | The customer should support the student team in preparing responses to RIDs and proposing a schedule for the identified actions, acting as an intermediary with the review team if needed | The customer can and should support the students in preparing answers to the review team by helping close any gap that inexperince may cause and help smooth the process, hence enhancing the educational return and maximizing the cahnces of technical success of the review.
ECSS-M-ST-10-01C | 5.3.4.a | A |  | Applicable
ECSS-M-ST-10-01C | 5.3.4.b | A |  | Applicable
ECSS-M-ST-10-01C | 5.3.4.c | A |  | Applicable
ECSS-M-ST-10-01C | 5.3.4.d | M | The review team leader shall prepare and issue the final review team report in conformance with the [DRD REQ N] and in accordance with the requirements of the review procedure. | The scope of the project type calls for a more streamline reporting of review results, thus the official DRD for the results report shall be substituted for a simplified version of the document
ECSS-M-ST-10-01C | 5.3.5.a | A |  | Applicable | Review Panel
ECSS-M-ST-10-01C | 5.4.a | A |  | Applicable | Review Process
ECSS-M-ST-10-01C | 5.4.b | A |  | Applicable
ECSS-M-ST-10-01C | 5.5.1.a | A |  | Applicable
ECSS-M-ST-10-01C | 5.5.2.a | A |  | Applicable
ECSS-M-ST-10-01C | 5.5.2.b | A |  | Applicable
ECSS-M-ST-10-01C | 5.5.3.a | A |  | Applicable
ECSS-M-ST-10-01C | 5.5.3.b | A |  | Applicable
ECSS-M-ST-10-01C | 5.5.4.a | A |  | Applicable
ECSS-M-ST-10-01C | 5.5.4.b | A |  | Applicable
ECSS-M-ST-10-01C | 5.5.5.a | A |  | Applicable
ECSS-M-ST-10-01C | 5.5.5.b | A |  | Applicable
ECSS-M-ST-10-01C | 5.5.6.a | D |  | Deleted. It is understood that given the scope of the porject type the review authority has direct overview of the close-out meeting and that its inputs will be already been taken into account. The meeting is deemed unnecessary a priori.
ECSS-M-ST-10-01C | 5.5.6.a | D |  | Deleted. It is understood that given the scope of the porject type the review authority has direct overview of the close-out meeting and that its inputs will be already been taken into account. The meeting is deemed unnecessary a priori.
ECSS-M-ST-10-01C | 5.6.a | A |  | Applicable | RID
ECSS-M-ST-10-01C | 5.6.b | A |  | Applicable
ECSS-M-ST-10-01C | 5.6.c | M | The content of the RID form shall conform to [REQ DRD Annex B] | The RID content should be streamlined and simplified in accordance to the scope of the project type and the educational objectives achieved by the review itself
ECSS-M-ST-10-01C | 5.6.d | M | The customer and supplier student team shall monitor all actions arising from the review | Given the more streamline connection between review team and supplier, the supplier is in this case expected to monitor the actions of the review
ECSS-M-ST-10-01C | 5.6.e | A |  | Applicable
ECSS-M-ST-10-01C | 5.6.f | A |  | Applicable
ECSS-M-ST-10-01C | 5.6.g | A |  | Applicable
ECSS-M-ST-10-01C | Annex A | A |  | Modified to be coherent with project scope. | Review DRD
ECSS-M-ST-10-01C | Annex B | M |  | Applicable
ECSS-M-ST-10-01C | Annex C | M |  | Modified aas indicated by the requirements 5.j to 5.n.1
ECSS-M-ST-10-01C | Annex D | D |  | Deleted
ECSS-M-ST-40C Rev1 | 5.2.1.1.a | M | Each supplier shall provide for customer’s approval a configuration management plan as part of its Project management Plan as per ECSS M ST 10C Annex A | Given the scope of the project-type the CM activities are severely degraded to the bare functional elements. The main objective is to track configuration changes for safety and relaibility towards other suppliers/customers interfacing with the project as well as transmitting crucial educational return on the concepts of CM and version tracking. Given this degraded state, the PMP will provide sufficient detail on the CM activities. | Configuration management General requirements
ECSS-M-ST-40C Rev1 | 5.2.1.1.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.2.1.a.1 | N | The CM activities shall be carried out by a clearly identified student team member | The responsability of CM must not be distributed amongst team members to prevent the activity from being sidelined
ECSS-M-ST-40C Rev1 | 5.2.1.a.2 | N | The CM activities should be combined into 1 unique role with the Documentation management role | Given the scope of the project the two roles heavily overlap and its normally advisable to combine them in one person
ECSS-M-ST-40C Rev1 | 5.2.1.a.3 | N | The CM activities can be combined with the Project Management role | Given the scope of the project, the possibility exists to combine the roles. This can be done when not enough man power is available or when the scope is particualrly small.
ECSS-M-ST-40C Rev1 | 5.2.1.2.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.2.1.2.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.2.1.2.c | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.2.1.2.d | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.2.1.3.a | A* |  | Given the educational objective of the project-types in question only certain documentation from the customer should be classified. As such, most classification requirements are applicable only to customer and/or academic entities as they are out of scope for the project-type
ECSS-M-ST-40C Rev1 | 5.2.1.3.b | A* |  | Given the educational objective of the project-types in question only certain documentation from the customer should be classified. As such, most classification requirements are applicable only to customer and/or academic entities as they are out of scope for the project-type
ECSS-M-ST-40C Rev1 | 5.2.1.3.c | A* |  | Given the educational objective of the project-types in question only certain documentation from the customer should be classified. As such, most classification requirements are applicable only to customer and/or academic entities as they are out of scope for the project-type
ECSS-M-ST-40C Rev1 | 5.2.1.3.d | A* |  | Given the educational objective of the project-types in question only certain documentation from the customer should be classified. As such, most classification requirements are applicable only to customer and/or academic entities as they are out of scope for the project-type
ECSS-M-ST-40C Rev1 | 5.2.1.3.e | A* |  | Given the educational objective of the project-types in question only certain documentation from the customer should be classified. As such, most classification requirements are applicable only to customer and/or academic entities as they are out of scope for the project-type
ECSS-M-ST-40C Rev1 | 5.2.1.3.f | A* |  | Given the educational objective of the project-types in question only certain documentation from the customer should be classified. As such, most classification requirements are applicable only to customer and/or academic entities as they are out of scope for the project-type
ECSS-M-ST-40C Rev1 | 5.2.1.3.g | A* |  | Given the educational objective of the project-types in question only certain documentation from the customer should be classified. As such, most classification requirements are applicable only to customer and/or academic entities as they are out of scope for the project-type
ECSS-M-ST-40C Rev1 | 5.2.1.3.h | A* |  | Given the educational objective of the project-types in question only certain documentation from the customer should be classified. As such, most classification requirements are applicable only to customer and/or academic entities as they are out of scope for the project-type
ECSS-M-ST-40C Rev1 | 5.2.2.a | D |  | Deleted in favor of a more streamlined and scope-appropiate requirement
ECSS-M-ST-40C Rev1 | 5.2.2.b | D |  | Deleted in favor of a more streamlined and scope-appropiate requirement
ECSS-M-ST-40C Rev1 | 5.2.2.c | D |  | Deleted in favor of a more streamlined and scope-appropiate requirement
ECSS-M-ST-40C Rev1 | 5.2.2.d | D |  | Deleted in favor of a more streamlined and scope-appropiate requirement
ECSS-M-ST-40C Rev1 | 5.2.2.e | D |  | Deleted in favor of a more streamlined and scope-appropiate requirement
ECSS-M-ST-40C Rev1 | 5.2.2.a.1 | N | Configuration management processes shall interface with the: 1. Project management activities, as related to planning, logistics and maintenance 2. Engineering activities, as related to technical information 3. Documentation Management activities for the identification, processing, control and distribution of documentation changes | Given the scope of the project-type, the interfaces of the CM activities can be synthesized greatly into one requirement
ECSS-M-ST-40C Rev1 | 5.3.1.1.a | A |  | Applicable | Configuration items and baseline
ECSS-M-ST-40C Rev1 | 5.3.1.2.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.1.2.b | D |  | The CI list will not be provided as document following any DRD, but rather as a subsection in the document containing the Product tree
ECSS-M-ST-40C Rev1 | 5.3.1.2.c | M | Identification of configuration items shall be produced at the PDR for customer approval in the document containing the product tree. | Modified to be coherence with deletion of ECSS-M-ST-40C Rev1 5.3.1.2.b
ECSS-M-ST-40C Rev1 | 5.3.1.3.a | A |  | Applicable. Although the list of documents required for the configuration baseline for the project type will be normally smaller than the lists provided and the usage of tailored documents such as DR would be coherent with this tailoring activity
ECSS-M-ST-40C Rev1 | 5.3.1.3.b | A |  | Applicable.
ECSS-M-ST-40C Rev1 | 5.3.1.4.a | M | Baselines shall be established at the conclusion of enforced technical reviews as the starting point for configuration control as defined below: The ICDs, TS and additional requirement documents are placed under configuration control after the PDR The Design Documentation (DDF, DJF or the combination in a DR) and DCL, DML, DPL, DMPL are placed under configuration control after the CDR All hardware, software and design is placed under configuration control after the QR | Given the scope of the project-type and the high probability to require configuration changes, the configuration control has to be employed strategically to not overencumber the project unnecessarily and allow the students the flexibility needed to develop the project and learn. Moreover, by keeping the most crucial aspects of the configuration baselines, as well as the incremental rationale form Requirements, to design, to hardware/software, the eductaional return desired is achieved.
ECSS-M-ST-40C Rev1 | 5.3.1.4.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.1.5.a | M | Any CI shall be identified to guarantee its traceability throughout the programme or project life cycle, providing: 1. A unique part number (PN) 2. A unique serial number (SN) if more than one instance of the same part number exists 3. Coherent reference to the PN or SN in all project documents | Modified to contain the most important aspects of the rest of the requirements of the superclass, to be coherent with the project-type scope
ECSS-M-ST-40C Rev1 | 5.3.1.5.b | D |  | Requirement deleted in deference of ECSS-M-ST-40C rev1 5.3.1.5.a as it encopases the general expectations of CI identification for all CI found in the project type. This will simplify and streamline the process.
ECSS-M-ST-40C Rev1 | 5.3.1.5.c | D |  | Requirement deleted in deference of ECSS-M-ST-40C rev1 5.3.1.5.a as it encopases the general expectations of CI identification for all CI found in the project type. This will simplify and streamline the process.
ECSS-M-ST-40C Rev1 | 5.3.1.5.d | D |  | Requirement deleted in deference of ECSS-M-ST-40C rev1 5.3.1.5.a as it encopases the general expectations of CI identification for all CI found in the project type. This will simplify and streamline the process.
ECSS-M-ST-40C Rev1 | 5.3.1.5.e | D |  | Requirement deleted in deference of ECSS-M-ST-40C rev1 5.3.1.5.a as it encopases the general expectations of CI identification for all CI found in the project type. This will simplify and streamline the process.
ECSS-M-ST-40C Rev1 | 5.3.1.5.f | D |  | Requirement deleted in deference of ECSS-M-ST-40C rev1 5.3.1.5.a as it encopases the general expectations of CI identification for all CI found in the project type. This will simplify and streamline the process.
ECSS-M-ST-40C Rev1 | 5.3.1.5.g | D |  | Requirement deleted in deference of ECSS-M-ST-40C rev1 5.3.1.5.a as it encopases the general expectations of CI identification for all CI found in the project type. This will simplify and streamline the process.
ECSS-M-ST-40C Rev1 | 5.3.1.5.h | D |  | Requirement deleted in deference of ECSS-M-ST-40C rev1 5.3.1.5.a as it encopases the general expectations of CI identification for all CI found in the project type. This will simplify and streamline the process.
ECSS-M-ST-40C Rev1 | 5.3.1.5.i | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.1.5.j | M | The identification marking methods applied shall be defined in the configuration management plan | All information regarding CM is to be provided in the tailored PMP, in the deciated section for CM
ECSS-M-ST-40C Rev1 | 5.3.1.5.k | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.1.6.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.1.6.b | D |  | Given the scope of the project type, this tayloring aims at not restricting the organization and file management of the student team to prevent overencumbering the development process.
ECSS-M-ST-40C Rev1 | 5.3.1.6.c | D |  | Given the scope of the project type, this tayloring aims at not restricting the organization and file management of the student team to prevent overencumbering the development process.
ECSS-M-ST-40C Rev1 | 5.3.1.6.d | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.1.6.e | D |  | Given the scope of the project type, this tayloring aims at not restricting the organization and file management of the student team to prevent overencumbering the development process.
ECSS-M-ST-40C Rev1 | 5.3.1.6.f | D |  | Given the scope of the project type, this tayloring aims at not restricting the organization and file management of the student team to prevent overencumbering the development process.
ECSS-M-ST-40C Rev1 | 5.3.1.6.g | A |  | Applicable. Made applicable to ensure version back-tracking given the high risk of incorrect configuration management by the students given their inexperience.
ECSS-M-ST-40C Rev1 | 5.3.1.6.h | D |  | Given the scope of the project type, this tayloring aims at not restricting the organization and file management of the student team to prevent overencumbering the development process.
ECSS-M-ST-40C Rev1 | 5.3.1.6.i | D |  | Given the scope of the project type, this tayloring aims at not restricting the organization and file management of the student team to prevent overencumbering the development process.
ECSS-M-ST-40C Rev1 | 5.3.1.6.j | D |  | Given the scope of the project type, this tayloring aims at not restricting the organization and file management of the student team to prevent overencumbering the development process.
ECSS-M-ST-40C Rev1 | 5.3.1.6.k | M | Digital data media shall be identified by the following: 1. File names 2. Version and issue 3. Date of generation | Modified to conatin only the crucial information. Upkeeping this three elements of document/configuration management would provide already great educational return and lies in a balance between overencumbering the students and maintaining some traceability and document control that makes overseeing the process feasible
ECSS-M-ST-40C Rev1 | 5.3.1.6.l | D |  | Given the scope of the project type, this tayloring aims at not restricting the organization and file management of the student team to prevent overencumbering the development process.
ECSS-M-ST-40C Rev1 | 5.3.2.1.a | A |  | Applicable | Configuration Control
ECSS-M-ST-40C Rev1 | 5.3.2.1.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.1.c | D |  | Out of scope for the project type given the supplier-customer chain scale and the particular relationship in terms of technical authority between Customer and Supplier
ECSS-M-ST-40C Rev1 | 5.3.2.1.d | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.1.e | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.2.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.2.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.2.c | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.2.d | D |  | The Non Conformance Control Methdology is not enforced as per ECSS Q ST 10 09 due to the scope of the project type, although Non Conformance Reporting is defined in other requirements made applicable by this tailoring activity
ECSS-M-ST-40C Rev1 | 5.3.2.2.e | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.2.f | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.2.g | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.2.h | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.2.i | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.3.a | M | All changes and change requests initiated by the customer shall be recorded in meeting minutes or written communication | Modified to reduce the complexity of communication. Given the educational relationship between customer and supplier, it is expected that many changes will be initiated by the customer as it steers the student team during the project's progression. The simplification of this process will make the communication easier
ECSS-M-ST-40C Rev1 | 5.3.2.3.b | M | All changes initiated by the supplier shall use a change proposal in conformance with what is stated in the CM plan in the PMP | The basic elements needed for a change request done by the students once under configuration control has to be clearly stated in the CM plan as well as the tracking mechanisms for this change requests
ECSS-M-ST-40C Rev1 | 5.3.2.4.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.4.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.4.c | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.5.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.6.a | M | The supplier shall request planned departures from requirements or design using a request for deviation in conformance with what is stated in the CM plan in the PMP | The basic elements needed for a deviation request done by the students once under configuration control has to be clearly stated in the CM plan as well as the tracking mechanisms for this deviation requests
ECSS-M-ST-40C Rev1 | 5.3.2.6.b | M | The supplier shall request unplanned departures from requirements or design using a request for waiver in conformance with what is stated in the CM plan in the PMP | The basic elements needed for a waiver request done by the students once under configuration control has to be clearly stated in the CM plan as well as the tracking mechanisms for this waiver requests
ECSS-M-ST-40C Rev1 | 5.3.2.6.c | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.6.d | D |  | Given the nature of the project type and the level of experience of the student teams, it is futile to stablish a limit to the deviations themselves.
ECSS-M-ST-40C Rev1 | 5.3.2.6.d | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.7.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.7.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.8.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.8.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.8.c | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.8.d | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.2.8.e | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.3.1.a | D |  | Given the scope of te project type, maintaning an accounting of the configuration baseline is not to be enforced. ECSS M ST 40C Rev1 5.3.1.6.f ensures that all prior configuration controlled items and baselines can be retrived, thus allowing when needed to produce an accounting. But to focus the educational return on the systematic tracking of changes , departures and waivers, the responsability lies on the customer to account for the configuration status if needed.
ECSS-M-ST-40C Rev1 | 5.3.3.1.b | D |  | Given the scope of te project type, maintaning an accounting of the configuration baseline is not to be enforced. ECSS M ST 40C Rev1 5.3.1.6.f ensures that all prior configuration controlled items and baselines can be retrived, thus allowing when needed to produce an accounting. But to focus the educational return on the systematic tracking of changes , departures and waivers, the responsability lies on the customer to account for the configuration status if needed.
ECSS-M-ST-40C Rev1 | 5.3.3.2.a | D |  | Given the scope of te project type, maintaning an accounting of the configuration baseline is not to be enforced. ECSS M ST 40C Rev1 5.3.1.6.f ensures that all prior configuration controlled items and baselines can be retrived, thus allowing when needed to produce an accounting. But to focus the educational return on the systematic tracking of changes , departures and waivers, the responsability lies on the customer to account for the configuration status if needed.
ECSS-M-ST-40C Rev1 | 5.3.3.2.b | D |  | Given the scope of te project type, maintaning an accounting of the configuration baseline is not to be enforced. ECSS M ST 40C Rev1 5.3.1.6.f ensures that all prior configuration controlled items and baselines can be retrived, thus allowing when needed to produce an accounting. But to focus the educational return on the systematic tracking of changes , departures and waivers, the responsability lies on the customer to account for the configuration status if needed.
ECSS-M-ST-40C Rev1 | 5.3.3.2.c | D |  | Given the scope of te project type, maintaning an accounting of the configuration baseline is not to be enforced. ECSS M ST 40C Rev1 5.3.1.6.f ensures that all prior configuration controlled items and baselines can be retrived, thus allowing when needed to produce an accounting. But to focus the educational return on the systematic tracking of changes , departures and waivers, the responsability lies on the customer to account for the configuration status if needed.
ECSS-M-ST-40C Rev1 | 5.3.3.2.d | D |  | Given the scope of te project type, maintaning an accounting of the configuration baseline is not to be enforced. ECSS M ST 40C Rev1 5.3.1.6.f ensures that all prior configuration controlled items and baselines can be retrived, thus allowing when needed to produce an accounting. But to focus the educational return on the systematic tracking of changes , departures and waivers, the responsability lies on the customer to account for the configuration status if needed.
ECSS-M-ST-40C Rev1 | 5.3.3.2.e | D |  | Given the scope of te project type, maintaning an accounting of the configuration baseline is not to be enforced. ECSS M ST 40C Rev1 5.3.1.6.f ensures that all prior configuration controlled items and baselines can be retrived, thus allowing when needed to produce an accounting. But to focus the educational return on the systematic tracking of changes , departures and waivers, the responsability lies on the customer to account for the configuration status if needed.
ECSS-M-ST-40C Rev1 | 5.3.3.2.f | D |  | Given the scope of te project type, maintaning an accounting of the configuration baseline is not to be enforced. ECSS M ST 40C Rev1 5.3.1.6.f ensures that all prior configuration controlled items and baselines can be retrived, thus allowing when needed to produce an accounting. But to focus the educational return on the systematic tracking of changes , departures and waivers, the responsability lies on the customer to account for the configuration status if needed.
ECSS-M-ST-40C Rev1 | 5.3.3.3.a | D |  | Given the scope of te project type, maintaning an accounting of the configuration baseline is not to be enforced. ECSS M ST 40C Rev1 5.3.1.6.f ensures that all prior configuration controlled items and baselines can be retrived, thus allowing when needed to produce an accounting. But to focus the educational return on the systematic tracking of changes , departures and waivers, the responsability lies on the customer to account for the configuration status if needed.
ECSS-M-ST-40C Rev1 | 5.3.3.3.b | D |  | Given the scope of te project type, maintaning an accounting of the configuration baseline is not to be enforced. ECSS M ST 40C Rev1 5.3.1.6.f ensures that all prior configuration controlled items and baselines can be retrived, thus allowing when needed to produce an accounting. But to focus the educational return on the systematic tracking of changes , departures and waivers, the responsability lies on the customer to account for the configuration status if needed.
ECSS-M-ST-40C Rev1 | 5.3.3.3.c | D |  | Given the scope of te project type, maintaning an accounting of the configuration baseline is not to be enforced. ECSS M ST 40C Rev1 5.3.1.6.f ensures that all prior configuration controlled items and baselines can be retrived, thus allowing when needed to produce an accounting. But to focus the educational return on the systematic tracking of changes , departures and waivers, the responsability lies on the customer to account for the configuration status if needed.
ECSS-M-ST-40C Rev1 | 5.3.4.1.a | D |  | As per this tailoring the SRR is not mandatory nor is the related configuration control enforced. This requirement is thus no longer applicable
ECSS-M-ST-40C Rev1 | 5.3.4.1.b | A |  | Applicable (If a PDR is conducted)
ECSS-M-ST-40C Rev1 | 5.3.4.1.c | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.4.2.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.4.2.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.4.2.c | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.5.a | D |  | Audits are considered out-of-scope for the project-type
ECSS-M-ST-40C Rev1 | 5.3.5.b | D |  | Audits are considered out-of-scope for the project-type
ECSS-M-ST-40C Rev1 | 5.3.6.a | M | The following product configuration related activities shall be implemented during the operational phase: 1. Preparation of a CM plan in conformance with instructions provided in ECSS M ST 10C Annex A], to meet the objective of the operational phase. NOTE This requirement can be fulfilled by adapting the development phase CM plan or creating a dedicated CM plan [...] | Adapted to refer to the Adapated PMP DRD that contains the information needed for the CM plan following this tailoring activity output
ECSS-M-ST-40C Rev1 | 5.3.7.1.a | A |  | Applicable | Document management
ECSS-M-ST-40C Rev1 | 5.3.7.1.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.1.c | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.1.d | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.1.e | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.1.f | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.2.1.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.2.1.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.2.1.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.2.1.c | M | The information/documentation content shall be established in accordance with the DRD or approved template which describes the document. | Customer apporved templates may be distributed to ease the process of conforming to requirements instead of refering exclusively to DRDs. These templates shall represent faithfully the DRD requirements and their preparation responsibility lies with the customer
ECSS-M-ST-40C Rev1 | 5.3.7.2.1.d | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.2.1.e | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.2.1.f | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.2.2.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.2.2.b | D |  | Out-of-scope for the project type. Information management particulars are left intentionally unregulated to not overrestrict the student team.
ECSS-M-ST-40C Rev1 | 5.3.7.2.2.c | D |  | Out-of-scope for the project type. Information management particulars are left intentionally unregulated to not overrestrict the student team.
ECSS-M-ST-40C Rev1 | 5.3.7.2.3.a | D |  | Out-of-scope for the project type. Information management particulars are left intentionally unregulated to not overrestrict the student team.
ECSS-M-ST-40C Rev1 | 5.3.7.2.3.b | D |  | Out-of-scope for the project type. Information management particulars are left intentionally unregulated to not overrestrict the student team.
ECSS-M-ST-40C Rev1 | 5.3.7.2.4.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.2.4.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.2.4.c | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.2.5.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.2.5.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.2.5.c | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.2.5.d | D |  | Out-of-scope for the project type. Information management particulars are left intentionally unregulated to not overrestrict the student team.
ECSS-M-ST-40C Rev1 | 5.3.7.3.1.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.1.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.1.c | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.1.d | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.1.e | D |  | No lower tier suppliers are present in the project type
ECSS-M-ST-40C Rev1 | 5.3.7.3.1.f | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.1.g | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.2.a | D |  | Given the scope and criticality of the project types, signature requirements are not enforced a priori. When strictly needed, the customer can make this requirement applicable. In all other cases, good-faith is expected from all parties and approval may be povided in written communciation or as part of meeting minutes
ECSS-M-ST-40C Rev1 | 5.3.7.3.2.b | D |  | Given the scope and criticality of the project types, signature requirements are not enforced a priori. When strictly needed, the customer can make this requirement applicable. In all other cases, good-faith is expected from all parties and approval may be povided in written communciation or as part of meeting minutes
ECSS-M-ST-40C Rev1 | 5.3.7.3.2.c | D |  | Given the scope and criticality of the project types, signature requirements are not enforced a priori. When strictly needed, the customer can make this requirement applicable. In all other cases, good-faith is expected from all parties and approval may be povided in written communciation or as part of meeting minutes
ECSS-M-ST-40C Rev1 | 5.3.7.3.2.d | D |  | Given the scope and criticality of the project types, signature requirements are not enforced a priori. When strictly needed, the customer can make this requirement applicable. In all other cases, good-faith is expected from all parties and approval may be povided in written communciation or as part of meeting minutes
ECSS-M-ST-40C Rev1 | 5.3.7.3.2.e | D |  | Given the scope and criticality of the project types, signature requirements are not enforced a priori. When strictly needed, the customer can make this requirement applicable. In all other cases, good-faith is expected from all parties and approval may be povided in written communciation or as part of meeting minutes
ECSS-M-ST-40C Rev1 | 5.3.7.3.2.f | D |  | Given the scope and criticality of the project types, signature requirements are not enforced a priori. When strictly needed, the customer can make this requirement applicable. In all other cases, good-faith is expected from all parties and approval may be povided in written communciation or as part of meeting minutes
ECSS-M-ST-40C Rev1 | 5.3.7.3.2.g | D |  | Given the scope and criticality of the project types, signature requirements are not enforced a priori. When strictly needed, the customer can make this requirement applicable. In all other cases, good-faith is expected from all parties and approval may be povided in written communciation or as part of meeting minutes
ECSS-M-ST-40C Rev1 | 5.3.7.3.3.a | D |  | Approval by process is not considered for the project-type
ECSS-M-ST-40C Rev1 | 5.3.7.3.3.b | D |  | Approval by process is not considered for the project-type
ECSS-M-ST-40C Rev1 | 5.3.7.3.3.c | D |  | Approval by process is not considered for the project-type
ECSS-M-ST-40C Rev1 | 5.3.7.3.3.d | D |  | Approval by process is not considered for the project-type
ECSS-M-ST-40C Rev1 | 5.3.7.3.3.e | D |  | Approval by process is not considered for the project-type
ECSS-M-ST-40C Rev1 | 5.3.7.3.4.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.4.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.4.c | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.4.d | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.4.e | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.4.f | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.5.a | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.5.b | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.5.c | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.5.d | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.5.e | A |  | Applicable
ECSS-M-ST-40C Rev1 | 5.3.7.3.6.a | D |  | Out-of-scope for the project type. Information management particulars are left intentionally unregulated to not overrestrict the student team.
ECSS-M-ST-40C Rev1 | 5.3.7.3.6.b | D |  | Out-of-scope for the project type. Information management particulars are left intentionally unregulated to not overrestrict the student team.
ECSS-M-ST-40C Rev1 | Annex A | A |  | Applicable. Integrated in PMP | Configuration Management DRD
ECSS-M-ST-40C Rev1 | Annex B | D |  | Out of scope for the project type
ECSS-M-ST-40C Rev1 | Annex C | D |  | Out of scope for the project type
ECSS-M-ST-40C Rev1 | Annex D | D |  | Out of scope for the project type
ECSS-M-ST-40C Rev1 | Annex E | D |  | Out of scope for the project type
ECSS-M-ST-40C Rev1 | Annex F | D |  | Out of scope for the project type
ECSS-M-ST-40C Rev1 | Annex G | D |  | Out of scope for the project type
ECSS-M-ST-40C Rev1 | Annex H | D |  | Out of scope for the project type
ECSS-M-ST-40C Rev1 | Annex I | D |  | Out of scope for the project type
ECSS-M-ST-40C Rev1 | Annex J | D |  | Out of scope for the project type
ECSS-M-ST-60C | 7.1.1.a | D |  | CBS is considered Out of scope for the project type. Requirements on budget reporting and preparation for reasons beyond the needs of the customer are not considered in this tailoring activity. | Cost Breakdown Structure
ECSS-M-ST-60C | 7.1.1.b | D |  | CBS is considered Out of scope for the project type. Requirements on budget reporting and preparation for reasons beyond the needs of the customer are not considered in this tailoring activity.
ECSS-M-ST-60C | 7.1.2.a | D |  | As per the project type definition, the buisness agreement if any is not done with respect of the WBS of the project thus rendering this requirement void
ECSS-M-ST-60C | 7.1.2.b | D |  | As per the project type definition, the buisness agreement if any is not done with respect of the WBS of the project thus rendering this requirement void
ECSS-M-ST-60C | 7.1.3.a | D |  | Out of scope for the project type.
ECSS-M-ST-60C | 7.1.3.b | D |  | Out of scope for the project type.
ECSS-M-ST-60C | 7.1.3.c | D |  | Out of scope for the project type.
ECSS-M-ST-60C | 7.2.a | A |  | Applicable | Risk management
ECSS-M-ST-60C | 7.2.b | A |  | Applicable
ECSS-M-ST-60C | 7.2.c | A |  | Applicable
ECSS-M-ST-60C | 8.1.a | A |  | Applicable | Project Schedule
ECSS-M-ST-60C | 8.1.b | A |  | Applicable
ECSS-M-ST-60C | 8.1.c | A |  | Applicable
ECSS-M-ST-60C | 8.1.d | A |  | Applicable
ECSS-M-ST-60C | 8.2.a | A |  | Applicable
ECSS-M-ST-60C | 8.2.b | D |  | Out of scope for the project type.
ECSS-M-ST-60C | 8.2.c | A |  | Applicable
ECSS-M-ST-60C | 8.2.d | A |  | Applicable
ECSS-M-ST-60C | 8.2.e | A |  | Applicable
ECSS-M-ST-60C | 8.2.f | A |  | Applicable
ECSS-M-ST-60C | 8.3.a | D |  | Schedule report in the form of a formal document is considered excessively formal for the project type. Update meetings and reviews will sufficie to monitor scheduling.
ECSS-M-ST-60C | 9.1.1.a | D |  | Given the strictly educational nature of the project type and the educational status of the project developping student team, all contractual and financial interface requirements are not applicable | Cost management and Budget
ECSS-M-ST-60C | 9.1.1.b | D |  | Given the strictly educational nature of the project type and the educational status of the project developping student team, all contractual and financial interface requirements are not applicable
ECSS-M-ST-60C | 9.1.2.a | D |  | Given the strictly educational nature of the project type and the educational status of the project developping student team, all contractual and financial interface requirements are not applicable
ECSS-M-ST-60C | 9.1.3.a | D |  | Given the strictly educational nature of the project type and the educational status of the project developping student team, all contractual and financial interface requirements are not applicable
ECSS-M-ST-60C | 9.1.4.a | D |  | Given the strictly educational nature of the project type and the educational status of the project developping student team, all contractual and financial interface requirements are not applicable
ECSS-M-ST-60C | 9.2.1.a | D |  | Given the scope of the project type, performing PCE and PCR exceeds the technical and educational needs. An adapted and streamlined requirement/s is provided instead
ECSS-M-ST-60C | 9.2.1.b | D
ECSS-M-ST-60C | 9.2.1.c | D
ECSS-M-ST-60C | 9.2.1.d | D
ECSS-M-ST-60C | 9.2.1.e | D
ECSS-M-ST-60C | 9.2.1.e.1 | N | The Budget section of the PMP as per ECSS M ST 10C Annex A shall conatin a cost estimation for the project projected costs as indicated in the DRD | New proposal of cost estimation requirement that refers to the adapated PMP DRD, which in turn calls for a breakdown of the cost estimation in categories as aligned with the WBS as possible, but without overrestricting the student etam given the low budgets and low amount of items to be controlled.
ECSS-M-ST-60C | 9.2.1.e.2 | N | The Budget section of the PMP as per ECSS M ST 10C Annex A shall conatin a cost accounting for the project incurred costs as indicated in the DRD | New proposal of cost accounting requirement that refers to the adapated PMP DRD, which in turn calls for a breakdown of the cost accounting in categories as aligned with the WBS as possible, but without overrestricting the student etam given the low budgets and low amount of items to be controlled.
ECSS-M-ST-60C | 9.2.2.a | D |  | Not applicable
ECSS-M-ST-60C | 9.2.3.a | D |  | Already covered by ECSS M ST 60C 9.2.1.e.1 and 9.2.1.e.2 in adequate scope
ECSS-M-ST-60C | 9.2.3.b | D |  | Already covered by ECSS M ST 60C 9.2.1.e.1 and 9.2.1.e.2 in adequate scope
ECSS-M-ST-60C | 9.2.4.a | D |  | Not applicable
ECSS-M-ST-60C | 9.2.5.a | D |  | Not applicable
ECSS-M-ST-60C | 9.2.5.b | D |  | Not applicable
ECSS-M-ST-60C | 9.2.5.c | D |  | Not applicable
ECSS-M-ST-60C | 9.2.6.a | D |  | Not applicable
ECSS-M-ST-60C | 9.2.6.b | D |  | Not applicable
ECSS-M-ST-60C | 9.3.1.1.a | D |  | Not applicable
ECSS-M-ST-60C | 9.3.1.1.b | D |  | Not applicable
ECSS-M-ST-60C | 9.3.1.1.c | D |  | Not applicable
ECSS-M-ST-60C | 9.3.1.2.a | D |  | Not applicable
ECSS-M-ST-60C | 9.3.2.a | D |  | Not applicable
ECSS-M-ST-60C | 9.3.3.1.a | D |  | Already covered by ECSS M ST 60C 9.2.1.e.1 and 9.2.1.e.2 in adequate scope
ECSS-M-ST-60C | 9.3.3.1.b | D |  | Already covered by ECSS M ST 60C 9.2.1.e.1 and 9.2.1.e.2 in adequate scope
ECSS-M-ST-60C | 9.3.3.1.c | D |  | Already covered by ECSS M ST 60C 9.2.1.e.1 and 9.2.1.e.2 in adequate scope
ECSS-M-ST-60C | 9.3.3.1.d | D |  | Already covered by ECSS M ST 60C 9.2.1.e.1 and 9.2.1.e.2 in adequate scope
ECSS-M-ST-60C | 9.3.3.1.e | D |  | Already covered by ECSS M ST 60C 9.2.1.e.1 and 9.2.1.e.2 in adequate scope
ECSS-M-ST-60C | 9.3.3.2.a | D |  | Already covered by ECSS M ST 60C 9.2.1.e.1 and 9.2.1.e.2 in adequate scope
ECSS-M-ST-60C | 9.3.4.a | D |  | Already covered by ECSS M ST 60C 9.2.1.e.1 and 9.2.1.e.2 in adequate scope
ECSS-M-ST-60C | 9.3.5.a | D |  | Not applicable
ECSS-M-ST-60C | 9.3.5.b | D |  | Not applicable
ECSS-M-ST-60C | 9.3.6.a | D |  | Not applicable
ECSS-M-ST-60C | 9.3.7.a | D |  | Not applicable
ECSS-M-ST-60C | 9.3.8.a | D |  | Not applicable
ECSS-M-ST-60C | 9.3.8.b | D |  | Not applicable
ECSS-M-ST-60C | 9.4.1.a | D |  | Not applicable
ECSS-M-ST-60C | 9.4.1.b | D |  | Not applicable
ECSS-M-ST-60C | 9.4.2.a | D |  | Not applicable
ECSS-M-ST-60C | 9.4.2.b | D |  | Not applicable
ECSS-M-ST-60C | 9.4.2.c | D |  | Not applicable
ECSS-M-ST-60C | Annex A | D |  | Not Applicable. See PMP DRD for further information | Cost and Schedule Management DRD
ECSS-M-ST-60C | Annex B | A |  | Applicable
ECSS-M-ST-60C | Annex C | D |  | Not Applicable
ECSS-M-ST-60C | Annex D | D |  | Not Applicable
ECSS-M-ST-60C | Annex E | D |  | Not Applicable
ECSS-M-ST-60C | Annex F | D |  | Not Applicable. See PMP DRD for further information
ECSS-M-ST-60C | Annex G | D |  | Not Applicable. See PMP DRD for further information
ECSS-M-ST-60C | Annex H | D |  | Not Applicable
ECSS-M-ST-60C | Annex I | D |  | Not Applicable
ECSS-M-ST-60C | Annex J | D |  | Not Applicable
ECSS-M-ST-60C | Annex K | D |  | Not Applicable
ECSS-M-ST-60C | Annex L | D |  | Not Applicable
ECSS-M-ST-60C | Annex M | D |  | Not Applicable
ECSS-M-ST-60C | Annex N | D |  | Not Applicable
ECSS-M-ST-60C | Annex O | D |  | Not Applicable
ECSS-M-ST-80C | 7.2.1.a | A |  | Overall applicable to all actors, risk management policy is responsbility of the customer given the particular relationship in existance with the student team as supplier and their lack of experience | Risk management
ECSS-M-ST-80C | 7.2.2.a | M | A risk management plan shall be established by each supplier as presented in the ECSS M ST 10C Annex A and to the level of detail requested therein | A risk management plan is needed and valuable for the students both from a technical and educational point of view, but it need not be extremely complex o overly detailed for the project-type scope
ECSS-M-ST-80C | 7.2.3.a | A |  | Applicable
ECSS-M-ST-80C | 7.2.4.a | A |  | Applicable
ECSS-M-ST-80C | 7.2.5.a | A |  | Applicable
ECSS-M-ST-80C | 7.2.6.a | A |  | Applicable
ECSS-M-ST-80C | 7.2.7.a | A |  | Applicable
ECSS-M-ST-80C | 7.2.8.a | A |  | Applicable
ECSS-M-ST-80C | 7.2.9.a | A |  | Applicable
ECSS-M-ST-80C | 7.2.10.a | A |  | Applicable
ECSS-M-ST-80C | 7.2.11.a | M | Risks shall be monitored, communicated, and results shall be displayed in regular meetings, written communication or reviews as applicable | The project type scope does not call for the use of a formal instrument like the RAR as requested by the original requirement
ECSS-M-ST-80C | 7.3.1.a | A |  | Applicable
ECSS-M-ST-80C | 7.3.1.b | D |  | Not applicable for the supplier-customer chain of the project-type
ECSS-M-ST-80C | 7.3.2.a | A |  | Applicable
ECSS-M-ST-80C | 7.3.3.a | A |  | Applicable
ECSS-M-ST-80C | 7.3.4.a | A |  | Applicable
ECSS-M-ST-80C | 7.3.5.a | A |  | Applicable
ECSS-M-ST-80C | Annex A | A* |  | Applicable to customer | Risk management DRD
ECSS-M-ST-80C | Annex B | D |  | Not Applicable
ECSS-M-ST-80C | Annex C | D |  | Not Applicable
ECSS-E-ST-10C Rev1 | 5.1.a | A* |  | The SEP requirememts are applicable but their fulfillment relies on the customer as they should have the expertise and authority to then translate this SEP directly or through instructions to the studnets. As such, the customer is expected to prepare and mantain an SEP in an adequate manner. | SEP
ECSS-E-ST-10C Rev1 | 5.1.b | A* |  | The SEP requirememts are applicable but their fulfillment relies on the customer as they should have the expertise and authority to then translate this SEP directly or through instructions to the studnets. As such, the customer is expected to prepare and mantain an SEP in an adequate manner.
ECSS-E-ST-10C Rev1 | 5.1.c | A* |  | The SEP requirememts are applicable but their fulfillment relies on the customer as they should have the expertise and authority to then translate this SEP directly or through instructions to the studnets. As such, the customer is expected to prepare and mantain an SEP in an adequate manner.
ECSS-E-ST-10C Rev1 | 5.1.d | A* |  | The SEP requirememts are applicable but their fulfillment relies on the customer as they should have the expertise and authority to then translate this SEP directly or through instructions to the studnets. As such, the customer is expected to prepare and mantain an SEP in an adequate manner.
ECSS-E-ST-10C Rev1 | 5.2.1.a | A |  | Applicable | Requirement Engineering
ECSS-E-ST-10C Rev1 | 5.2.1.b | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.2.1.c | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.2.1.d | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.2.1.e | M | The system engineering function shall ensure that each requirement for the lower level elements has a justification reflected in the Technical requirement specification. | Given the scope of the project type, the TS is expected to contain the declaration and justification of all of the project's requirements
ECSS-E-ST-10C Rev1 | 5.2.2.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.2.2.b | D |  | A RTM exceeds the scope of the project type
ECSS-E-ST-10C Rev1 | 5.2.2.c | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.2.3.1.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.2.3.1.b | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.2.3.1.c | M | The system engineering function shall establish a specification tree in the DR as requested by ECSS-E-ST-10C Rev1 Annex B.1 | The specification tree DRD is adapated and simplified to the project type scope and then integrated into the DR
ECSS-E-ST-10C Rev1 | 5.2.3.2.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.2.3.2.b | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.2.3.3.a | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | 5.2.3.3.b | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.2.3.3.c | D |  | Out of scope for the proejct type given dispositions on risk management
ECSS-E-ST-10C Rev1 | 5.2.3.4.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.2.3.4.b | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.2.3.5.a | D |  | Given the project type there are no lower levels for requirement allocation
ECSS-E-ST-10C Rev1 | 5.2.3.6.a | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | 5.2.3.6.b | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | 5.2.3.7.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.2.3.8.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.2.3.8.b | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | 5.2.3.9.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.1.a | D |  | Deleted as Phase 0 lies out of the scope of the project type | System Analysis
ECSS-E-ST-10C Rev1 | 5.3.1.b | M | The system engineering function shall perform a functional analysis, produce the functional architecture, and produce the function tree as stated in ECSS-E-ST-10C Rev1 Annex B.1 | Function tree is integrated into the Design Report
ECSS-E-ST-10C Rev1 | 5.3.1.c | M | The system engineering function shall document the functional architecture in the design report as stated in ECSS-E-ST-10C Rev1 Annex B.1 | The DDF and DJF are combined into the DR. As such, all requirements affecting either document, if applicable, are traspassed to the DR
ECSS-E-ST-10C Rev1 | 5.3.1.d | M | The system engineering function shall justify the functional architecture in the design report as stated in ECSS-E-ST-10C Rev1 Annex B.1 | The DDF and DJF are combined into the DR. As such, all requirements affecting either document, if applicable, are traspassed to the DR
ECSS-E-ST-10C Rev1 | 5.3.1.e | M | The system engineering function shall perform a physical analysis, produce the physical architecture and produce the product tree in conformance with ECSS-M-ST-10 Rev1 5.3.a | Adpated for internal coherence
ECSS-E-ST-10C Rev1 | 5.3.1.f | M | The system engineering function shall document the physical architecture in the design report as stated in ECSS-E-ST-10C Rev1 Annex B.1 | The DDF and DJF are combined into the DR. As such, all requirements affecting either document, if applicable, are traspassed to the DR
ECSS-E-ST-10C Rev1 | 5.3.1.g | M | The system engineering function shall justify the physical architecture in the design report as stated in ECSS-E-ST-10C Rev1 Annex B.1 | The DDF and DJF are combined into the DR. As such, all requirements affecting either document, if applicable, are traspassed to the DR
ECSS-E-ST-10C Rev1 | 5.3.1.h | D |  | Out of scope for the project type
ECSS-E-ST-10C Rev1 | 5.3.1.i | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.1.j | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.2.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.2.b | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.2.c | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.2.d | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.2.e | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.3.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.3.b | A | The system engineering function shall evaluate alternative concepts, designs and solutions against each other in a Trade-off report section in the DRD | Trade-offs are degraded and integrated into the DR. No formal Trade-off reporting is requested given the scope of the project type
ECSS-E-ST-10C Rev1 | 5.3.3.c | D |  | Out of Scope for the project-type
ECSS-E-ST-10C Rev1 | 5.3.4.a | A |  | Supplier does not develop an SEP for the project type
ECSS-E-ST-10C Rev1 | 5.3.4.b | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.4.c | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.4.d | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.4.e | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.4.f | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.4.g | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.3.4.h | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.4.1.1.a | A |  | Applicable | Design and configuration
ECSS-E-ST-10C Rev1 | 5.4.1.1.b | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.4.1.1.c | D |  | Supplier-Customer chain only has 1 level for the project type
ECSS-E-ST-10C Rev1 | 5.4.1.1.d | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.4.1.1.e | D |  | Out of scope for the project type
ECSS-E-ST-10C Rev1 | 5.4.1.1.f | D |  | Out of scope for the project type
ECSS-E-ST-10C Rev1 | 5.4.1.2.a | A |  | Applicable. Budgets are integrated into the DR DRD
ECSS-E-ST-10C Rev1 | 5.4.1.2.b | A |  | Applicable. Budgets are integrated into the DR DRD
ECSS-E-ST-10C Rev1 | 5.4.1.2.c | A |  | Applicable. Budgets are integrated into the DR DRD
ECSS-E-ST-10C Rev1 | 5.4.1.3.a | D |  | Supplier does not develop an SEP for the project type
ECSS-E-ST-10C Rev1 | 5.4.1.3.b | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.4.1.3.c | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.4.1.3.d | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.4.1.3.e | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.4.1.3.f | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.4.1.4.a | D |  | Deleted in favor of 5.4.1.4.a.1
ECSS-E-ST-10C Rev1 | 5.4.1.4.b | D |  | Deleted in favor of 5.4.1.4.a.2
ECSS-E-ST-10C Rev1 | 5.4.1.4.a.1 | N | The system engineering function shall establish and maintain in the DR, as per ECSS-E-ST-10C Rev1 Annex B.1: 1. The design definition 2. The design justification In lieu of the respective DDJ and DDF | New requirement create to state the need to create and maintain a DR
ECSS-E-ST-10C Rev1 | 5.4.1.4.c | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.4.2.1.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.4.2.1.b | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.4.2.1.c | M | The system engineering function shall ensure that the configuration is documented in the DR and in configuration definition documents | Modified to harmonize with DR
ECSS-E-ST-10C Rev1 | 5.4.2.2.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.4.2.3.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.4.2.3.b | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | 5.5.1.a | M | The system engineering function shall define the Verification Plan in accordance with the MAIVP DRD and coordinate the product verification accordingly | Modified to refer to adapted version of VP in the form of MAIVP | Verification
ECSS-E-ST-10C Rev1 | 5.5.2.a | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | 5.5.2.b | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.5.2.c | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.5.2.d | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.5.2.e | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | 5.5.2.f | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.6.1.a | D |  | Out of scope for the project type | System engineering integration and control
ECSS-E-ST-10C Rev1 | 5.6.1.b | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | 5.6.1.c | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | 5.6.1.d | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | 5.6.1.e | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | 5.6.1.f | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.6.1.g | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.6.2.a | D |  | Supplier does not develop an SEP for the project type
ECSS-E-ST-10C Rev1 | 5.6.3.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.6.3.b | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.6.3.c | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.6.4.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.6.4.b | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | 5.6.4.c | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | 5.6.5.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.6.5.b | D |  | Supplier does not develop an SEP for the project type
ECSS-E-ST-10C Rev1 | 5.6.7.a | D |  | Out of scope for the project type
ECSS-E-ST-10C Rev1 | 5.6.7.b | D |  | Out of scope for the project type
ECSS-E-ST-10C Rev1 | 5.6.7.c | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.6.7.b | A |  | Out of scope for the project type
ECSS-E-ST-10C Rev1 | 5.6.7.c | A |  | Out of scope for the project type
ECSS-E-ST-10C Rev1 | 5.6.7.d | A |  | Out of scope for the project type
ECSS-E-ST-10C Rev1 | 5.6.7.e | A |  | Out of scope for the project type
ECSS-E-ST-10C Rev1 | 5.6.7.f | A |  | Out of scope for the project type
ECSS-E-ST-10C Rev1 | 5.6.7.g | A |  | Out of scope for the project type
ECSS-E-ST-10C Rev1 | 5.6.8.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.6.8.b | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | 5.6.8.c | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.6.9.a | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.6.9.b | A |  | Applicable
ECSS-E-ST-10C Rev1 | 5.6.9.c | A |  | Applicable
ECSS-E-ST-10C Rev1 | Annex B | D |  | Not applicable for the phasing of the project type | System Engineering DRD
ECSS-E-ST-10C Rev1 | Annex C | D |  | Not applicable for the project type
ECSS-E-ST-10C Rev1 | Annex D | A* |  | Applicable to customer
ECSS-E-ST-10C Rev1 | Annex E | D |  | Not applicable for the project type
ECSS-E-ST-10C Rev1 | Annex F | D |  | Not applicable for the project type
ECSS-E-ST-10C Rev1 | Annex G | A |  | Applicable. Adapted and integrated into DR DRD
ECSS-E-ST-10C Rev1 | Annex H | A |  | Applicable. Adapted and integrated into DR DRD
ECSS-E-ST-10C Rev1 | Annex I | A |  | Applicable. Adapted and integrated into DR DRD
ECSS-E-ST-10C Rev1 | Annex J | A |  | Applicable. Adapted and integrated into DR DRD
ECSS-E-ST-10C Rev1 | Annex K | A |  | Applicable. Adapted and integrated into DR DRD
ECSS-E-ST-10C Rev1 | Annex L | A |  | Applicable. Adapted and integrated into DR DRD
ECSS-E-ST-10C Rev1 | Annex M | N/A |  | Deleted from ECSS
ECSS-E-ST-10C Rev1 | Annex N | D |  | Not applicable for the project type
ECSS-E-ST-10C Rev1 | Annex O | D |  | Integrated entirely into the TS DRD
ECSS-E-ST-10C Rev1 | Annex P | A |  | Applicable
| Annex B.1 | N |  | DRD for DR. Create to integrate DDF and DJF | Verification Planning
ECSS-E-ST-10-02C Rev1 | 5.2.1.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.1.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.1.c | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.1.d | M | The verification approach shall be defined by the supplier in the Manufacturing, Integration Verification Plan (MAIVP) for approval by the customer prior to implementation. | Modified to harmonize with MAIVP approach
ECSS-E-ST-10-02C Rev1 | 5.2.1.e | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.2.1.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.2.1.b | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.2.2.1.c | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.2.2.1.d | D |  | Not Applicable for the project type scope
ECSS-E-ST-10-02C Rev1 | 5.2.2.1.e | D |  | Not Applicable for the project type scope
ECSS-E-ST-10-02C Rev1 | 5.2.2.2.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.2.2.b | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.2.2.2.c | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.2.2.2.d | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.2.2.2.e | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.2.2.2.f | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.2.2.2.g | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.2.2.3.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.2.3.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.2.3.c | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.2.3.d | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.2.3.e | D |  | Not applicable for the project type scope
ECSS-E-ST-10-02C Rev1 | 5.2.2.3.f | D |  | Not applicable for the project type scope
ECSS-E-ST-10-02C Rev1 | 5.2.2.4.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.2.4.b | D |  | Not applicable for the project type scope
ECSS-E-ST-10-02C Rev1 | 5.2.2.4.c | D |  | Not applicable for the project type scope
ECSS-E-ST-10-02C Rev1 | 5.2.2.5.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.2.5.b | D |  | Not applicable for the project type scope
ECSS-E-ST-10-02C Rev1 | 5.2.3.a | M | Verification shall be accomplished through the verification levels in conformance with those defined with the MAIVP DRD [MAIVP DRD REQ] | Modified to harmonize with MAIVP approach
ECSS-E-ST-10-02C Rev1 | 5.2.3.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.3.c | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.1.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.1.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.1.c | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.1.d | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.2.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.2.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.2.c | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.2.d | D |  | Not applicable for the project type scope
ECSS-E-ST-10-02C Rev1 | 5.2.4.3.1.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.3.1.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.3.2.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.3.2.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.4.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.4.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.5.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.5.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.5.c | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.5.d | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.5.e | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.2.4.6.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.4.6.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.5.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.6.1.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.6.1.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.6.1.c | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.2.6.1.d | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.6.2.a | D |  | Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.2.6.2.b | D |  | Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.2.6.2.c | D |  | Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.2.6.2.d | D |  | Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.2.6.4.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.6.5.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.6.5.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.6.6.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.7.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.7.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.7.c | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.7.d | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.7.e | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.7.f | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.7.g | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.8.1.a | M | The supplier shall provide a Manufacturing, Integration Verification Plan (MAIVP) for the reviews as agreed with the customer
ECSS-E-ST-10-02C Rev1 | 5.2.8.1.b | D |  | Redundant with ECSS E ST 10 02C Rev1 5.5.1.a
ECSS-E-ST-10-02C Rev1 | 5.2.8.2.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.8.2.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.2.8.3.a | D |  | Redundant with ECSS E ST 10 02C Rev1 5.5.1.a
ECSS-E-ST-10-02C Rev1 | 5.2.8.3.b | D |  | Redundant with ECSS E ST 10 02C Rev1 5.5.1.a | Verification Execution and reporting
ECSS-E-ST-10-02C Rev1 | 5.3.1.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.3.1.b | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.3.1.c | D |  | Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.3.1.d | D |  | Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.3.2.1.a | D |  | Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.3.2.1.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.3.2.1.c | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.3.2.1.d | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.3.2.2.a | D |  | Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.3.2.2.b | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.3.2.2.c | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.3.2.2.d | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.3.2.3.a | D |  | Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.3.2.3.b | D |  | RoD shall be conducted directly by customer by inspection of the design documentation. RoD reports are not to be expected for the project type scope
ECSS-E-ST-10-02C Rev1 | 5.3.2.3.c | D |  | RoD shall be conducted directly by customer by inspection of the design documentation. RoD reports are not to be expected for the project type scope
ECSS-E-ST-10-02C Rev1 | 5.3.2.3.d | D |  | RoD shall be conducted directly by customer by inspection of the design documentation. RoD reports are not to be expected for the project type scope
ECSS-E-ST-10-02C Rev1 | 5.3.2.4.a | D |  | Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.3.2.4.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.3.2.4.c | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.3.2.4.d | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.3.2.5.a | D |  | Multiple reports can be generated instead of a VR. Intention is to reduce generation of extra classes of documents
ECSS-E-ST-10-02C Rev1 | 5.3.2.5.b | D |  | Multiple reports can be generated instead of a VR. Intention is to reduce generation of extra classes of documents
ECSS-E-ST-10-02C Rev1 | 5.3.2.5.c | D |  | Multiple reports can be generated instead of a VR. Intention is to reduce generation of extra classes of documents
ECSS-E-ST-10-02C Rev1 | 5.3.2.5.d | D |  | Multiple reports can be generated instead of a VR. Intention is to reduce generation of extra classes of documents
ECSS-E-ST-10-02C Rev1 | 5.3.2.6.a | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.3.2.6.b | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.3.2.6.c | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.3.2.6.d | N/A |  | Deleted from ECSS
ECSS-E-ST-10-02C Rev1 | 5.3.2.6.e | A |  | Applicable | Verification Control and close-out
ECSS-E-ST-10-02C Rev1 | 5.4.1.a | D |  | Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.4.1.b | D |  | Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.4.1.c | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.4.1.d | A |  | Applciable
ECSS-E-ST-10-02C Rev1 | 5.4.2.a | D |  | VCB is considered Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.4.2.b | D |  | VCB is considered Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.4.2.c | D |  | VCB is considered Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.4.2.d | D |  | VCB is considered Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.4.2.e | D |  | VCB is considered Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.4.2.f | D |  | VCB is considered Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.4.2.g | D |  | VCB is considered Out of scope for the project type
ECSS-E-ST-10-02C Rev1 | 5.4.3.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.4.3.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.4.4.1.a | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.4.4.1.b | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.4.4.1.c | M | The intermediate issues of the Verification Control Document (VCD), reflecting the current status of the verification database, shall be made available to the customer upon request | Modified to Customer instead of VCB as customer will approve the verification given the inexperience of the supplier
ECSS-E-ST-10-02C Rev1 | 5.4.4.1.d | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | 5.4.4.1.e | M | The final issue of the Verification Control Document (VCD) shall be submitted to the customer after the approval of the last report, within the time frame agreed with the customer. | Modified to Customer instead of VCB as customer will approve the verification given the inexperience of the supplier
ECSS-E-ST-10-02C Rev1 | 5.4.4.2.a | A |  | Applicable | Verification DRD
ECSS-E-ST-10-02C Rev1 | Annex A | A |  | Applicable. Integrated in MAIVP
ECSS-E-ST-10-02C Rev1 | Annex B | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | Annex C | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | Annex D | D |  | RoD shall be conducted directly by customer by inspection of the design documentation. RoD reports are not to be expected for the project type scope
ECSS-E-ST-10-02C Rev1 | Annex E | A |  | Applicable
ECSS-E-ST-10-02C Rev1 | Annex F | D |  | Multiple reports can be generated instead of a VR. Intention is to reduce generation of extra classes of documents | Technical Requirement Specification
ECSS-E-ST-10-06C | 7.2.1.a | A |  | Applicable
ECSS-E-ST-10-06C | 7.2.1.b | A |  | Applicable
ECSS-E-ST-10-06C | 7.2.2.a | D |  | Out of scope for the project type. Supplier is always the responsible party in this case
ECSS-E-ST-10-06C | 7.2.2.b | D |  | Out of scope for the project type. Supplier is always the responsible party in this case
ECSS-E-ST-10-06C | 7.2.3.a | A |  | Applicable.
ECSS-E-ST-10-06C | 7.2.3.b | A |  | Applicable.
ECSS-E-ST-10-06C | 7.2.3.a | A |  | Applicable.
ECSS-E-ST-10-06C | 7.2.3.c | A |  | Applicable.
ECSS-E-ST-10-06C | 7.2.3.d | A |  | Applicable.
ECSS-E-ST-10-06C | 7.2.3.e | A |  | Applicable.
ECSS-E-ST-10-06C | 7.2.4.a | A |  | Applicable.
ECSS-E-ST-10-06C | 7.2.4.b | A |  | Applicable.
ECSS-E-ST-10-06C | 7.2.4.c | A |  | Applicable.
ECSS-E-ST-10-06C | 7.2.4.d | A |  | Applicable.
ECSS-E-ST-10-06C | 7.2.5.a | A |  | Applicable.
ECSS-E-ST-10-06C | 7.2.6.a | A |  | Applicable.
ECSS-E-ST-10-06C | 7.2.7.a | A |  | Applicable.
ECSS-E-ST-10-06C | 7.2.8.a | A |  | Applicable. | Requirement Specification
ECSS-E-ST-10-06C | 8.2.1.a | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.1.b | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.2.a | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.2.b | D |  | Out of scope for the project type. Supplier is always the responsible party in this case
ECSS-E-ST-10-06C | 8.2.2.c | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.3.a | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.3.b | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.3.c | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.4.a | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.5.a | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.6.a | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.6.b | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.6.c | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.6.d | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.7.a | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.8.a | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.9.a | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.9.b | A |  | Applicable.
ECSS-E-ST-10-06C | 8.2.10.a | A |  | Applicable.
ECSS-E-ST-10-06C | 8.3.1.a | A |  | Applicable.
ECSS-E-ST-10-06C | 8.3.1.b | A |  | Applicable.
ECSS-E-ST-10-06C | 8.3.2.a | A |  | Applicable.
ECSS-E-ST-10-06C | 8.3.2.b | A |  | Applicable.
ECSS-E-ST-10-06C | 8.3.2.c | A |  | Applicable.
ECSS-E-ST-10-06C | 8.3.2.d | A |  | Applicable.
ECSS-E-ST-10-06C | 8.3.3.a | A |  | Applicable. | TS DRD
ECSS-E-ST-10-06C | Annex A | A |  | Applicable. | Interface management
ECSS-E-ST-10-24C Rev1 | 5.1.a | A* |  | Applicable to interface responsible
ECSS-E-ST-10-24C Rev1 | 5.1.b | A* |  | Applicable to interface responsible
ECSS-E-ST-10-24C Rev1 | 5.1.c | A* |  | Applicable to interface responsible
ECSS-E-ST-10-24C Rev1 | 5.1.d | A* |  | Applicable to interface responsible
ECSS-E-ST-10-24C Rev1 | 5.1.e | A* |  | Applicable to interface responsible | Interface Identification and requirements
ECSS-E-ST-10-24C Rev1 | 5.2.a | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.2.b | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.2.c | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.2.d | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.3.a | A* |  | Applicable to interface responsible
ECSS-E-ST-10-24C Rev1 | 5.3.b | A* |  | Applicable to interface responsible
ECSS-E-ST-10-24C Rev1 | 5.3.c | A* |  | Applicable to interface responsible
ECSS-E-ST-10-24C Rev1 | 5.3.d | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.3.e | A |  | Applicable | Interface Definition
ECSS-E-ST-10-24C Rev1 | 5.4.a | A* |  | Applicable to interface responsible
ECSS-E-ST-10-24C Rev1 | 5.4.b | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.4.c | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.4.d | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.4.e | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.4.f | A |  | Applicable | Interface Control and Verification
ECSS-E-ST-10-24C Rev1 | 5.5.a | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.5.b | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.5.c | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.5.d | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.5.e | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.5.f | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.5.g | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.6.a | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.6.b | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.6.c | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.6.d | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.6.e | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | 5.6.f | A |  | Applicable | Interface DRD
ECSS-E-ST-10-24C Rev1 | Annex A | A* |  | Applicable to interface responsible
ECSS-E-ST-10-24C Rev1 | Annex B | A |  | Applicable
ECSS-E-ST-10-24C Rev1 | Annex C | A |  | Applicable